## Sheet1
Ministry of Sports and Youth Affairs
Sports Division
Master Procurrement Plan - January to April 2020
Department/ Line Agency/ Ministry | Procurement Category (Goods, works & Services etc) | Estimated Cost (Rs. Mn) | Source of Financing/ name of the Donor | Procurement method (ICB, LIB, LNB, NCB and National Shopping etc.) | Level of Authority | Priority status U = Urgent P= Priority N= Normal | Current status of procurement preparedness activities | Scheduled date of commencement | Scheduled date of completion | Remarks
Ministry of Sports and Youth Affairs Sports Division | Works | 10
| Construction of Maliyadeva Fire & Achary range - Stage II | 10 | GOSL | NCB | MPC | P | Pending | 2020.02.15 | 2020.04.30
| Goods | 48.13
| Kitchen Equipment - Nuwara Eliya Sports Complex | 2.5 | GOSL | National Shopping (STC & Other) | MPC | P | On going | 2019:10 | 2020:02 | STC & Other
| 100 Hand rollers | 15 | GOSL | NCB | MPC | P | Pending | 2020:01 | 2020:06
| 35 concreate pitch mat | 9 | GOSL | NCB | MPC | P | Pending | 2020.01.15 | 2020.05.30
| Development of St. Anthoney Boy's College Pavillian | 20 | GOSL | NCB | MPC | P | Pending | 2020.01.15 | 2020.05.30
| Office Equpment & furniture | 0.13 | GOSL | National Shopping | MPC | P | List Out | 2020.01.30 | 2020.04.30
| Stationary & Toner | 1.5 | GOSL | National Shopping | MPC | P | List Out | 2020.01.01 | 2020.04.30
| Services | 18.7
| Vehical Repair | 2.5 | GOSL | NCB & Shoppong | MPC | U | On going | 2020.01.01 | 2020.04.30
| Services & Maintence of Computers | 1.1 | GOSL | NCB & Shoppong | MPC | U | On going | 2020.01.01 | 2020.04.30
| Service & Maintence Of Ac,Lift,Generator &Electric Systems | 1.2 | GOSL | NCB & Shoppong | MPC | U | On going | 2020.01.01 | 2020.04.30
| Security Services | 3.2 | GOSL | NCB | MPC | P | On going | 2020.01.01 | 2020.04.30
1
Department/ Line Agency/ Ministry | Procurement Category (Goods, works & Services etc) | Estimated Cost (Rs. Mn) | Source of Financing/ name of the Donor | Procurement method (ICB, LIB, LNB, NCB and National Shopping etc.) | Level of Authority | Priority status U= Urgent P= Priority N= Normal | Current status of procurement preparedness activities | Scheduled date of commencement | Scheduled date of completion | Remarks
| Cleaning Services | 3.5 | GOSL | NCB | MPC | P | On going | 2020.01.01 | 2020.04.30
| Water bill & Electricity bill | 4.5 | GOSL | NCB | MPC | P | On going | 2020.01.01 | 2020.04.30
| Postal & Communication | 1 | GOSL | National Shopping | MPC | P | On going | 2020.01.01 | 2020.04.30
| Transport | 1 | GOSL | National Shopping | MPC | P | On going | 2020.01.01 | 2020.04.30
| Rent & Local Taxes | 0.5 | GOSL | National Shopping | MPC | P | Ongoing | 2020.01.01 | 2020.04.30
| Others | 0.2 | GOSL | National Shopping | MPC | P | Pending | 2020.01.01 | 2020.04.30
2